## Sheet1
Description | Who? | March 23-29 | March 30 April 5 | April 6-12 | April 13-19 | April 20-26 | April 27 - May 3 | May 4-10 | May 11-17 | May 18/19 | Extended description
Create new 3D engine | René | [9 empty] | Create a new 3D engine using lwjgl
Create new 2D engine | René and Jean | [9 empty] | Add 2D options to the engine for UI
Project structure | René and Ivan | [9 empty] | Make sure that the project structure is clear and flexible
Redo UI | Jean | [9 empty] | Create an improved version of the phase 1 UI in the new engine
Connection UI and backend | René, Jean and Ivan | [9 empty] | Make sure that the back- and frontend can properly communicate
Have a playable game (for humans) | Ivan | [9 empty] | Have a working game where you can at least shoot the ball and score
Second order Verlet solver | Matthijs | [9 empty] | Implement the second order Verlet solver for physics
Classical 4th order Runge Kutta solver | Matthijs |  |  | in class | [6 empty] | Implement the classical 4th order Runge kutta solver for physics
Bouncing against trees (phase 3) | Matthijs | [9 empty] | Add the physics for bouncing against trees, including hit detection
Basic bot research | Aaron and Ivan | [9 empty] | Figure out how a bot should work to meet the requirements for phase 2
Basic version of basic bot | Aaron and Ivan | [9 empty] | Create a first version of the bot for phase 2 that can already meet the requirements
Finished basic bot | Aaron and Ivan | [9 empty] | Improve the bot further and fix any problems that the bot may have
Research advanced bot (phase3) | Aaron and Ivan | [9 empty] | Come up with an improved bot by doing research
Get started with advanced bot (phase3) | Aaron and Ivan | [9 empty] | Start the implementation of this improved bot
Course designer basics (phase 3) | René | [9 empty] | Enable the user to customize the terrain by adding sand and trees
Course designer finished, including saving/loading (phase 3) | René | [9 empty] | Add a save and load option to the course designer
Improved terrain and water | René | [9 empty] | Improve the visuals for the terrain and water
3D UI improvements (ball reset preview, shot direction indicator) | René and Jean | [9 empty] | Add 3D UI for resetting the ball and indicating in which direction you're shooting
Music/sound effects | Haoran | [9 empty] | Add music that plays while playing the game and add sound effects to actions like shooting and scoring
Consider flying balls (phase 3 prep) | Matthijs | [9 empty] | Add the physics for flying balls and make sure the rest of the game still works when this is used
Start with report (mainly structure) | Jean, Matthijs and René | [9 empty] | Prepare an outline for the report in LaTeX and learn LaTeX if needed