## Sheet1
Description | Who? | March 23-29 | March 30 April 5 | April 6-12 | April 13-19 | April 20-26 | April 27 - May 3 | May 4-10 | May 11-17 | May 18/19 | Extended description
MAJOR BUILDS / MILESTONES
Basic working game | [10 empty] | Working 3D engine, basic 2D UI options (text and images), 3D physics, the ability to shoot the ball and score (possibly with UI, but not necessarily), basic course designer (you can add and remove trees)
Editor build | [10 empty] | Fully functional course editor, including adding and removing both trees and sand. It also has the ability to save and load a terrain.
Basic bot | [10 empty] | A basic version of the bot that can already win the game with a simple course
Improved physics engine | [10 empty] | The new physics solvers are implemented and working
Full-fledged bot | [10 empty] | The final both for this phase is working as intended
PROJECT STRUCTURE AND PHASE 1 FIXES
Improve the graphics engine structure | René | [9 empty] | Make sure that the project structure is clear and flexible, focusing on the graphicsc engine's structure
Improve the physics engine structure | Ivan | [9 empty] | Make sure that the project structure is clear and flexible, focusing on the physics engine's structure
Redo UI | Jean | [9 empty] | Create an improved version of the phase 1 UI in the new engine
Main menu | [10 empty] | Redo main menu
Shooting the ball | [10 empty] | Redo shooting the ball UI
Resetting after hitting water | [10 empty] | Redo resetting after hitting the water UI
Editor | [10 empty] | Create editor UI (loading and saving options as well as key bindings explained)
Connection UI and backend | René, Jean and Ivan | [9 empty] | Make sure that the back- and frontend can properly communicate (if I click this button, run this code)
Main menu
Shooting the ball
Resetting after hitting water
Editor
Have a playable game (for humans) | Ivan | [9 empty] | Have a working game where you can at least shoot the ball and score
Redoing inputOutputModule | René and Aaron | [9 empty] | Have to option to save and load the game information (start location, terrain info, etc)
GRAPHICS ENGINE
Create new 2D engine basis | René | [9 empty] | Add the option to add 2D elements to the UI
Create new 3D engine | René | [9 empty] | Create a new 3D engine using lwjgl
Show a triangle | [10 empty] | Be able to show a colored triangle in 2D
Add lighting | [10 empty] | Add per pixel lighting and specular lighting
Camera system in 3D | [10 empty] | Add a camera in 3D that can be moved around
Allow 3D shapes | [10 empty] | Have the ability to create models in 3D by code
Import 3D models | [10 empty] | Allow importing 3D objects from Blender
Basic terrain system (flat ground) | [10 empty] | Create a system to deal with terrain rendering (specialized code, separate from other 3D objects)
Terrain with height | [10 empty] | Add height to the terrain
Multiple textures for the terrain | [10 empty] | Allow for multiple textures to be applied to the terrain (grass and sand)
Skybox | [10 empty] | Add a skybox
Cursor to point on terrain | [10 empty] | Convert a mouse click onto coordinates on the terrain
Spawn objects on clicked location | [10 empty] | Add an object with the position being the point that was clicked on the terrain
Water system | [10 empty] | Add water to the game with reflection, fresnel effect and 'movement'
Course designer basics (phase 3) | René | [9 empty] | Enable the user to customize the terrain by adding sand and trees
Course designer finished, including saving/loading (phase 3) | René | [9 empty] | Add a save and load option to the course designer
Expand 2D engine with buttons, textfields and a file explorer | Jean | [9 empty] | Expand 2D engine with buttons, textfields and a file explorer
3D UI improvements (ball reset preview, shot direction indicator) | René | [9 empty] | Add 3D UI for resetting the ball and indicating in which direction you're shooting
Ball reset preview | [10 empty] | Show where the ball would end up after resetting it when you hit the water
Shot direction indicator | [10 empty] | Add a vector pointing to the shot direction from ball itself
Additional engine improvements (shadows, improved AA) | Haoran | [9 empty] | Implement some additional and optional engine improvements
Physics
Second order Verlet solver | Matthijs | [9 empty] | Implement the second order Verlet solver for physics
Classical 4th order Runge Kutta solver | Matthijs | [9 empty] | Implement the classical 4th order Runge kutta solver for physics
Bouncing against trees (phase 3 prep) | Matthijs | [9 empty] | Add the physics for bouncing against trees, including hit detection
Consider flying balls (phase 3 prep) | Matthijs | [9 empty] | Add the physics for flying balls and make sure the rest of the game still works when this is used
SOUND
Music/sound effects | Haoran | [9 empty] | Add music that plays while playing the game and add sound effects to actions like shooting and scoring
BOT
Basic bot research | Aaron and Ivan | [9 empty] | Figure out how a bot should work to meet the requirements for phase 2
Basic version of basic bot | Aaron and Ivan | [9 empty] | Create a first version of the bot for phase 2 that can already meet the requirements
Hole in one if possible | [10 empty] | If you can score in one shot, do so
Handle more than one shot to win | [10 empty] | If you need multiple shots to score than the bot has to be able to do this
Improve heuristics | [10 empty] | Improve heuristics to optimize the bot's behavior and performance
Finished basic bot | Aaron and Ivan | [9 empty] | Improve the bot further and fix any problems that the bot may have
Research advanced bot (phase3) | Aaron and Ivan | [9 empty] | Come up with an improved bot by doing research
Get started with advanced bot (phase3) | Aaron and Ivan | [9 empty] | Start the implementation of this improved bot
REPORT
Start with report (mainly structure) | Jean, Matthijs and René | [9 empty] | Prepare an outline for the report in LaTeX and learn LaTeX if needed
PRESENTATION
Create the presentation | Everyone
Planned duration
Finished earlier than planned
Critically behind on schedule
Possible extension
Disaster