## Sheet1
René | Create 3D engine, create basis of 2D engine, improve project structure, expand 3D UI, 3D course designer, course desginer save/load system, improved terrain and water rendering
Aaron | Support Ivan with the bot (research and implementation for basic and advanced bot)
Ivan | Improve project structure, ensure that we have a playable game, bot research and development (basic and advanced)
Jean | Expand 2D engine, redo 2D UI, connection UI and backend
Matthijs | Second order Verlet solver, classic 4th order Runge Kutta solver, bouncing against trees, consider flying balls
Haoran | Music and sound effect, 'mutliplayer'
Description | March 23-29 | March 30 April 5 | April 6-12 | April 13-19 | April 20-26 | April 27 - May 3 | May 4-10 | May 11-17 | May 18/19
Create new 3D engine
Create new 2D engine
Project structure
Redo UI
Connection UI and backend
Have a playable game (for humans)
Second order Verlet solver
Classical 4th order Runge Kutta solver |  |  | in class
Bouncing against trees
Basic bot research
Basic version of basic bot
Finished basic bot
Research advanced bot (phase3)
Get started with advanced bot (phase3)
Course designer basics (phase 3)
Course designer finished, including saving/loading (phase 3)
Improved terrain and water
3D UI improvements (ball reset preview, shot direction indicator)
Music/sound effects
Multiplayer (turn based or switch after goal?)
Consider flying balls (phase 3 prep)
Start with report (mainly structure)